## Sheet1
| Category | Description | Originator | Impact
R1 | Time-Related | Very limited time available in semester for such a large project. | S. Long | 1
R2 | Operational | Other obligations interfering with our time to work on the project. | P. Singh | 1
R3 | Technical | Not developing a well-functioning database. | S. Long | 1
R4 | Operational | Failure in communication between team members. | P. Singh | 1
R5 | Operational | We have a small team with limited expertise as we are still learning the technologies necessary to complete the project. | S. Long | 2
R6 | Functional | Inability to deliver a product that the product owner is satisfied with. | C. Blake | 3
R7 | Design | Risk of choosing incorrect architecture. | P. Singh | 4
R8 | Design | Difficulties in creating a user-friendly but secure product. | S. Long | 2
R9 | Bugdet | Risk of acquiring necessary resources for a shopping cart utility. | C. Blake | 2
R10 | Technical | Inability to create a successful tiered account system. | P. Singh | 3
R11 | Functional | Market risk that this product will not catch on with users. | C. Blake | 3

## RIS1
Risk ID: 1 | Date: 2/1/2019 | Prob: 90% | Impact: Catastrophic
Description: There are many features that need to be implemented on a very tight schedule.
Refinement/context: Subcondition 1: Must determine what can be done in a tight time frame.
Mitigation/Monitoring: 1. Meet with Dr. Banks for guidance. 2. Contact product owner to reset expectations. 3. Agree on what major components can be completed within our time frame. 4. Prioritize and manage necessary tasks.
Management/Contingency Plan/trigger: Develop a detailed set of tasks needed to complete necessary components of the product.
Current status: 2/1/2019: Meeting with Dr. Banks initiated.
Originator: S. Long | Assigned: C. Blake

## RIS2
Risk ID: 2 | Date: 2/1/2019 | Prob: 60% | Impact: Catastrophic
Description: Personal life and busy college life is a road block
Refinement/context: Subcondition 1: we should manage the personal life and college, to get enough time for the project.
Mitigation/Monitoring: 1. Everyday schedule 2. Try to keepup with project everyday for atleast 30 minutes. 3. Make short task to perform everyday to keep going.
Management/Contingency Plan/trigger: Everyone should monitor everyone, and help everyone in everything.
Current status: 2/4/2019: Completing everyday task and following schedule strictly
Originator: P Singh | Assigned: S. Long

## RIS3
Risk ID: 3 | Date: 2/5/2019 | Prob: 30% | Impact: Catastrophic
Description: Creating a database which is not completely functional for all of our data would cause strain on the project as a whole. The entirity of the website will need to interface with the database.
Refinement/context: Subcondition 1: Must decide the appropriate database management system. Subcondition 2: Knowledge constraints when working with chosen management system. Subcondition 3: Proper interfacing needs to be established between the website and the database.
Mitigation/Monitoring: 1. Establish meetings with Dr. Watson to discuss databases. 2. Read the database management systems manuals and watch tutorials. 3. Properly check each teammembers code contributions pertaining to the database.
Management/Contingency Plan/trigger: Thoroughly discuss our intentions with the database to Dr. Watson for comments and concerns. Potential scrapping and rewritting of the database. Trigger: Mitigation steps unproductive as of 2/20/2019
Current status: 2/5/2019: Mitigation Steps Initiated
Originator: S. Long | Assigned: P. Singh

## RIS4
Risk ID: 4 | Date: 02/05/2019 | Prob: 30% | Impact: Catastrophic
Description: Everyone is busy. There is no good way to keep in touch for this kind of project.
Refinement/context: Must communicate everyday and discuss the progress day to day.
Mitigation/Monitoring: 1. Atleast two member should meet everyday to discuss the work. 2. The one who completed the daily task should help the other mate to complete. 3. Try to be patient and be friendly in this situation to avoid conflicts.
Management/Contingency Plan/trigger:
Current status: 2/5/2019 Still trying to keep up with Plans and schedule.
Originator: P. Singh | Assigned: C. Blake

## Blank_RIS
Risk ID: | Date: | Prob: | Impact:
Description:
Refinement/context:
Mitigation/Monitoring:
Management/Contingency Plan/trigger:
Current status:
Originator: | Assigned: